## Template - Phase 2
R - Responsible | Completes the deliverable or task.
A - Accountable | Makes final decisions and signs off on task completion. Only 1 per task.
C - Consulted | An advisor, stakeholder, or subject matter expert who offers guidance before an action is taken.
I - Informed | Kept up to date on decisions made.
Plant Pals Landing Page | Role A | Role B | Role C | Role D | Role E | Role F
PHASE 2
Task/Deliverable
Task/Deliverable 1
Task/Deliverable 2
Task/Deliverable 3
Task/Deliverable 4
Task/Deliverable 5
Task/Deliverable 6

## Activity
R - Responsible | Completes the deliverable or task.
A - Accountable | Makes final decisions and signs off on task completion. Only 1 per task.
C - Consulted | An advisor, stakeholder, or subject matter expert who offers guidance before an action is taken.
I - Informed | Kept up to date on decisions made.
Plant Pals Landing Page | Web Manager | Graphic Designer | Web Developer | Quality Assurance Tester | Content Writer | Web Designer
PHASE 2
Task/Deliverable
Design a landing page | A | R | I | I | C | C
Create a landing page mockup | A | C | C | I | I | R
Design image assets | C | R | I | C | I | A
Write content | A | I | C | C | R | I
Code the landing page | A | C | R | I | I | C
Test the landing page | A | I | C | R | I | C