## Template - Phase 1
R - Responsible | Completes the deliverable or task.
A - Accountable | Makes final decisions and signs off on task completion. Only 1 per task.
C - Consulted | An advisor, stakeholder, or subject matter expert who offers guidance before an action is taken.
I - Informed | Kept up to date on decisions made.
Plant Pals Marketing & Sales Strategy | Role A | Role B | Role C | Role D | Role E | Role F
PHASE 1
Task/Deliverable
1. Task/Deliverable
2. Task/Deliverable
3. Task/Deliverable
4. Task/Deliverable

## Activity
R - Responsible | Completes the deliverable or task.
A - Accountable | Makes final decisions and signs off on task completion. Only 1 per task.
C - Consulted | An advisor, stakeholder, or subject matter expert who offers guidance before an action is taken.
I - Informed | Kept up to date on decisions made.
Plant Pals Marketing & Sales Strategy | Director of Product | Marketing Manager | Marketing Coordinator | Copywriter | Head of Sale | Sales Manager
PHASE 1
Task/Deliverable
1. Create a marketing plan for the new service | C | A | R |  | I
2. Write promotional copy |  | C | A | R | I
3. Design marketing assets (e.g., flyers, brochures, and online advertisements) | C | A | C | R | I | I
4. Create a customer outreach and onboarding plan | C | I |  |  | A | R

## Exemplar - Phase 1
R - Responsible | Completes the deliverable or task.
A - Accountable | Makes final decisions and signs off on task completion. Only 1 per task.
C - Consulted | An advisor, stakeholder, or subject matter expert who offers guidance before an action is taken.
I - Informed | Kept up to date on decisions made.
Plant Pals Marketing & Sales Strategy | Director of Product | Marketing Manager | Marketing Coordinator | Copywriter | Head of Sales | Sales Manager
PHASE 1
Task/Deliverable
1. Create a marketing plan for the new service | C | A | R | C | C | I
2. Write promotional copy | I | A | C | R | I | I
3. Design marketing assets | I | A | R | C | I | I
4. Create a customer outreach and onboarding plan | C | C | I | I | A | R
*Note: The Director of Product should be kept informed about the promotional copy and the marketing assets. Other informed individuals may vary.