## WBS Spreadsheet
Milestone | Task ID | Task | Owner | Duration (days) | Notes
Establish plant delivery and logistics plan | 1.1 | Source packaging materials | Fulfillment Director
| 1.2 | Hire delivery drivers | Human Resources Specialist
| 1.3 | Calculate delivery fees | Financial Analyst
Select and install supply chain software and equipment | 2.1 | Supervise vendor setup of inventory & fulfillment software | Inventory Manager
| 2.2 | Supervise vendor installation of fulfillment equipment | Fulfillment Director
| 2.3 | Determine safety protocols | Quality Assurance Tester
Plan an employee training program | 3.1 | Develop training sessions | Human Resources Specialist
| 3.2 | Train employees to use the new software and equipment | Training Manager
| 3.3 | Monitor employee progress & improve training processes | Training Manager