## Status Report
Project Name: Plant Pals Operations
Today's date: July 5
Summary |  |  |  | Overall Status (RAG)
We have installed new software to keep track of incoming orders and begun sending out the first test batch of Plant Pals to customers. However, we have run into issues with product quality, customer communication, and the delivery process. Our next milestones include sending the test batch customers newsletters on plant upkeep and sending out the second batch of plants. This report also includes top risks and issues that have arisen and how we intend to take action. |  |  |  | Amber
Completed Tasks and Milestones
Description | Date | Status | Owner |  | Comments
Installation of new software | June 15 | Completed | IT Specialist |  | The installation took three days longer than expected.
Began sending test batches of Plant Pals orders to customers | June 21 | Completed | The Fulfillment Director |  | The number of orders exceeded targets by 15%.
Upcoming Tasks and Milestones
Description | Date | Status | Owner |  | Comments
Send the first batch customers e-newsletters on how to take care of their plants. | July 7 | Upcoming | IT Specialist |  | The newsletter must follow Office Green’s brand design guidelines.
Hit the delivery dates at leavt by 95% | July 19 | Upcoming | Fulfillment Director |  | The error rate should be under 5%.
Top Risks and Issues
Issue |  | Impact | Action |  |  | Owner
10% of the plants are not properly potted. |  | Profit loss, complaints, and budget issues | Ensure plants are properly potted and verified before shipment |  |  | Warehouse Operations Manager
The customer relations team is receiving only 30% of requests and complaints |  | Customer dissatisfaction | Fix problems with new customer service software
Delivery drivers are not available for delivering all the plants |  | Customers cancellig the suscription | Hire and train more delivery drivers |  |  | HR Specialist