## Tasks and Timeline
Sauce & Spoon Project Plan
| TASK |  | START DATE | DUE DATE | DURATION | TASK OWNER | STATUS | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
|  | NOTES | [5 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Milestone: Tablets received
| Generate quotes and review costs |  |  |  | 14 | bar: WEEK 1 F to WEEK 2 T
| Create contracts and statements of work for vendors | Use past contracts for boilerplate |  |  | 5 | bar: WEEK 1 F to WEEK 2 T
| Order tablets | Shipping updated to ~10 days |  |  | 10 | bar: WEEK 2 W
2 | Milestone: Training complete
| Manager training planning |  |  |  | 5 | bar: WEEK 4 M to WEEK 4 R
| Manager training | One day event |  |  | 1 | bar: WEEK 4 M to WEEK 4 R
| GM meeting with staff regarding buy-in | Let Gilly plan this |  |  | 1 | bar: WEEK 4 F to WEEK 5 F
| Waitstaff training planning |  |  |  | 5
| Waitstaff training | One day event |  |  | 1
3 | Milestone: Tablet installation complete
| Book an electrician to install the tablets/wiring | Reference from Deanna |  |  | 8
| Install working tablets in the bar area at the Downtown restaurant locations |  |  |  | 1
| Install working tablets in the bar area at the North restaurant locations |  |  |  | 1
| Sync tablet software with POS | Need to update the POS system |  |  | 7
4 | Milestone: Launch Day complete
| Create a launch day plan: staffing, troubleshooting, etc. |  |  |  | 20
| Upload branding to tablets | Connect the marketing team to Terrific Tablets |  |  | 10
| Load menus into the tablets | Waiting on Carter |  |  | 7
| Include messaging about payment security on the tablet | Uploading text |  |  | 1
| Create a behind-the-scenes video of the scratch-to-table process to show on the tablets |  |  |  | 14
| Create a procedure for securing tablets at the end of the night (at the table or in a safe) |  |  |  | 13
| Create and implement a post-dining survey to assess customer satisfaction |  |  |  | 3
| Test run planning |  |  |  | 10
| Test run | One day event |  |  | 1
| Launch day | One day event |  |  | 1

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | CONFIDENCE RATING (H/M/L) | KNOWN DATES
Order Tablets |  | 9 | 7 | 8 | 10 | M
Prepare Menu Items and Coupon Values | Carter is owning | 12 | 10 | 12 | 14 | L
Update POS System |  | 3 | 2 | 3 | 4 | M
Software Installation |  | 1 | 0.5 | 0.6 | 1 | H

## Additional Resouces
Additional Resources
Title | Link | Date Added | Notes

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria met?
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  | Question answer options
Criteria/Description | Survey question | Question type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5