## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | Went well | Customer satisfaction | More than 72$ customers rated 4+ ratings
Customers | Went well | Waiters assistance | 76% people are happy with assistance from waiters
Customers | Went well | Food preparation | 72% received correct orders
Customers | Went well | Checkout process | 82% said checkout process was easy
Customers | Needs improvement | Birthday Club | 84% didn't signup for birthday club | Need to promote birthday club and offer discounts
Customers | Needs improvement | Table waiting time | Customers waited 15+ minutes for tables availability | Need to reduce table turn time
Customers | Needs improvement | Food preparation time | 44% of customers received their food after 20 mins | Add more kitchen staff to proces the orders quickly
Project team | Went well | Tablets installment
Project team | Needs improvement | Table turnout time
Project team | Needs improvement | Incorrect Orders | Few orders were sent back | Need to receive proper instructions before finalising order.
Project team | Went well | met most of our customer satisfaction standards.
Project team | Needs improvement | Birthday Club | Less interest | working with the designer to update the content on the website and the tablets so it’s clearer what the program is, what we’re asking, and how people can participate
Project team | Needs improvement | Planning Training | operational issues during planning | we want to do a better job of understanding each location’s history before planning gets underway.
Project team | Needs improvement | tablet implementation took longer |  | we plan things properly based on everyone’s availability.